## Slide 1
The Global Polio Program’s Successes and Remaining Challenges
18th Meeting of the IMB, 29 June 2020

## Slide 2: Presentation Sections
Implications of the COVID-19 Pandemic on Polio Eradication
Progress in Afghanistan and Pakistan
Africa WPV Polio-Free Certification, Nigeria update and cVDPV2 Outbreaks
Annex: Additional slides

## Slide 3
Implications of the COVID-19 Pandemic on Polio Eradication
Section 1

## Slide 4: Outline
COVID-19 context
Initial GPEI response & support for the pandemic response
Impact: surveillance, SIAs/EI, public perception
Risk assessment and SIAs resumption efforts
Financial Status
Challenges / opportunities and next steps

## Slide 5: COVID-19 Context
I - Emergency Phase
(March– June 2020?)
- SIAs halted globally
- Critical GPEI functions continuing
II - Resumption Phase
(July/ Aug…)
- SIAs Resumption in outbreaks & WPV endemics (in coordination with EI)
III – Post/Para pandemic Phase (time ?)
- significantly lower COVID-19 risk
- long-term revisions to Endgame Strategy 2019-23
Anticipated Pandemic Evolution
AFR
Source: WHE
EMR
Source: WHE

## Slide 6: Overall / Immediate Program Adaptation
Initial GPEI POB guidance (24 March)
  suspend all immunization activities in alignment with WHO global guidance on response to COVID-19
  critical functions such as PV surveillance should continue
GPEI capacities supporting the pandemic response
  Surveillance, GPLN, data management, risk communication
  >31k staffs / contractors
SC established a ‘continuity Planning & Facilitation Group (PFG)’
  to develop short term workplan & coordinate efforts within GPEI & with EI / other programs
EMR POL Surv. Network Support
AFR Country Support Map
(AFR dashboard)

## Slide 7
Impact on Surveillance
Source: POLIS
Widespread & significant impact on polio surveillance sensitivity
  Decrease in case detection in WPR, SEAR, EMR
  Decrease/halt of ES in several countries in SEAR & EMR
  Major disruption in shipment of specimen in AFR
  All 21 high-risk countries (including endemics, outbreak COs) are being impacted
Multiple Polio staff members across regions diagnosed with COVID-19
Need for strategic planning to ramp up to pre-COVID-19 levels
  Implications of additional funding needs & technical support
% drop in AFP Reporting; April 2019 vs April 2020
% of Expected ES Samples Collected & Processed, by month 2020
(June data not complete)

## Slide 8
Impact on EI & Polio SIAs (as of end-May 2020)
Per GPEI / WHO guidance, all polio SIAs suspended
EPI not widely suspended but disrupted in many countries
Source: POLIS
Number of SIAs impacted by region; March-May 2020
Vaccine supplies (worth $6m) already in countries
100 million doses (worth $12.5m) procured & awaiting delivery due to interruptions
Some of above with short-medium shelf-life
Some suppliers reaching storage capacity & may stop production
Source: WHO

## Slide 9: Impact on Communications
Global public perception has shifted
  In countries with substantial polio assets, this infrastructure was instrumental in pandemic response, but COVID-19 is a “setback” for GPEI
‘Infodemic’ with impact on all vaccination programmes
  abundance of (mis)information and rumours in digital spaces and communities
Health behaviors
  Polio risk perception vs. COVID, communities more likely to refuse polio vaccine without other services they consider more urgent
Concerns of front line workers on re-start of SIAs
  PPEs, perceptions of safety, virus transmission

## Slide 10: GPEI Updated Guidance (21 May), Promoting SIAs Resumption
Simulated impact of Pause in AFG/PAK
Exponential rise in cVDPV2 cases if a response is not initiated
Based on risk analysis & intensifying PV transmission
  immediate SIAs restart planning in endemics, OB countries & resumption after risk-benefit analysis (WHO/GPEI Framework for Decision Making issued)
  safety of FLWs & community is paramount
  Preventive SIAs to resume when local situation permits
  Stresses coordination with other progs.
Preventive SIAs schedules available & OBR scheduling underway
  Ops./financial planning in process
  GPEI - EI coordinating on integration
2019
2020
cVDPV2 in 90 additional districts in AFR by end July. ~200% increase, if response is not resumed

## Slide 11: Program’s Financial Status
In line with ‘POB’s Call to Action’; GPEI capacities (HR, logistical, lab., comms.) fully mobilized to support COVID-19 response
  Translating to approx. $20m / month
Significant impact of COVID-19 pandemic
  Program will have to make up for the lost ground
  Consideration for safety of FLWs & communities; i.e. PPE, preventive measures, training needs etc.
  10% - 15% “COVID premium” being applied to the budgets
Resultantly, higher revised program costs expected in future

## Slide 12: Challenges
Uncertainties related to Pandemic
  COVID-19 epidemiology vis-à-vis polio program planning
  Variable national & sub-national situations
Surveillance gaps
Declining immunity / potential for rapidly expanding outbreaks
Unprecedented challenges towards high quality SIAs
  IPC / PPE, communications
  Community engagement
Use the pause for reviewing the ‘game plan’
Leverage
  Global discourse on COVID-19 for importance of vaccination
  National Govts’ commitment & GPEI’s support for pandemic response
Momentum to integrate approaches (GPEI + EI + Essential services); win-win
  PEI targets, response timelines etc. to be considered
Opportunities

## Slide 13: Key Priorities / Next Steps
Anticipate the ‘new normal’ & review program strategies at all levels
  operational adjustments (IPC/PPE, training etc.) / flexible approaches
  Put community and FLWs at center of prototyping re-start of SIAs
Finalize endemics & outbreak SIAs calendar
  aiming restart during mid – end July 2020
Strengthen GPEI–EI / EHS links to capture available ‘joint working’ opportunities
  possible ‘add- ons’ & integration
Risk Communication with donors & public
Prioritize nOPV2 development & rollout
Technical/ operational support to address the identified surveillance gaps

## Slide 14
Overall Progress in Afghanistan and Pakistan
Section 2

## Slide 15: Afghanistan and Pakistan Outline
Current context, challenges and opportunities
cVDPV2 and WPV1 epidemiology and risk modeling
Resuming mass vaccination in context of COVID-19
Polio programme priorities for Pakistan and Afghanistan

## Slide 16: Current context, challenges and opportunities
COVID-19
  COVID response a priority at all levels (government, community)
  Polio infrastructure and workforce fully engaged in response, but also affected
  SIAs paused since March, interruption of health services with impact on routine immunization and polio surveillance
  Movement restrictions and fear in communities affecting health seeking behaviour
Opportunities
  Leveraging robust all-of-government response to COVID
  Changing community perception and acceptance through polio FLW involvement in COVID response
Polio programme continuity
  Programme continuity plans put in place to preserve essential functions
  Surveillance activities maintained, SOPs adjusted for COVID context
Co-circulation of WPV1 and cVDPV2
  Threat of exponential spread of cVDPV2 by late summer
  Continued WPV1 transmission and spread
WPV/cVDPV2 Infected districts during last 6 months

## Slide 17: Current context, challenges and opportunities
Pakistan polio programme transformation
  Acceleration and increasing ownership of transformation
  Eradication as a shared priority across the political divide
  Shift from PEI-EPI synergy to integration under one leadership
  Laser focus on super high-risk Union Councils
  Communication for Eradication Strategic Framework developed
  Review of Community Based Vaccination programme conducted
Complex and fluid political context in Afghanistan
  General elections and political instability
  US-Taliban peace talks
  Change of senior leadership in Ministry of Public Health
Ban on mass vaccination in Afghanistan
  Continued ban on polio mass vaccination in large parts of the country by anti-government elements (AGE)
  Integrated services plan developed targeting 10 districts of the South

## Slide 18
cVPDV2 epidemiology
Geographic expansion of cVDPV2
Expansion of transmission in Pakistan
Spread into Eastern Region of Afghanistan
Three instances of breakthrough transmission after mOPV2 SIAs in Pakistan
cVDPV2 modeling projections
High risk for a very large nationwide outbreak (>1,000 cases) if no SIAs with type 2 containing oral vaccine in 2020
100 cases
Simulated cumulative number of cVDPV2 cases
1 Jun 2020
Simulated cVDPV2 transmission and cumulative cases by:
1 Aug 2020
1 Jul 2020
cVDPV2 case
Number of cVDPV2 infections
Number of cVDPV2 infections
Number of cVDPV2 infections
cVDPV2 cases 2019-2020

## Slide 19
WPV1 epidemiology
Ongoing widespread WPV1 transmission
South KP becoming new WPV1 reservoir
Core reservoirs of in Karachi and Quetta block with persistent transmission
Expansion of WPV1 to previously polio free areas (Sindh and Punjab in Pakistan; West and North of Afghanistan)
No WPV1 detected in core reservoirs in Peshawar/Khyber >6 months
WPV1 modeling projections
Hundreds of cases (>500) by end 2020 if no SIAs with type 1 containing oral vaccine in 2020
WPV1 Cases & ES+, by Cluster, 2020

## Slide 20: Resuming mass vaccination in context of COVID
Urgent need to resume SIAs safely
  Response to cVDPV2 immediate priority while maintaining control of WPV1 transmission
  Both countries geared for resumption of SIAs in July
  Strong political commitment at all levels required
  Understanding and addressing community concerns essential
  Design SIAs within broader delivery of services (COVID response/recovery, immunization, other essential health needs)
  Clear and credible communication of rationale for SIA resumption
  Operational and tactical adjustments: Guidance developed to mitigate incremental risk of COVID to frontline workers and the community
Use the unprecedented national and political mobilization for COVID response and lessons learned to resume and strengthen the national programmes to finally achieve polio eradication

## Slide 21: Pakistan and Afghanistan programme priorities
Eliminate cVDPV2 in 2020 without exacerbating COVID-19
Garner political and national mobilization for COVID-19 in support of polio eradication at all levels
Pakistan
Maintain control of WPV1 through targeted campaigns and outbreak response
Complete the transformation of polio eradication programme
Maintain focus on super high-risk Union Councils (SHRUCs)
Afghanistan
Interrupt WPV1 transmission in non-reservoir areas
All efforts to gain and maintain access for full-scale mass vaccination activities
Endemic areas of Southern Region
  Accessible areas: Improve quality of vaccination activities
  Areas where mass vaccination is banned: Implement all possible immunization activities

## Slide 22
Africa WPV Polio-Free Certification, Nigeria update and
cVDPV2 Outbreaks
Section 3

## Slide 23
The final four countries in the Africa region--Cameroon, Central African Republic, Nigeria and South Sudan--were certified as free of wild polio virus by the Africa Regional Certification Commission (ARCC) on 18 June 2020.
The Commission will make a final decision on certifying the Africa region as free of WPV by August 2020, after a satisfactory review of updated reports from the other 43 countries in the WHO Africa Region. If certified, it would be the fifth of the six WHO regions to have eliminated wild poliovirus.
The ARCC also thanked the polio program for its support to the COVID-19 response, but noted concern with routine immunization coverage, the urgency need to stop cVPDV2 outbreaks and to continue efforts to strengthen surveillance.
Africa Region Nearing WPV Polio-Free

## Slide 24: Nigeria Update
In June 2020 ARCC certifies Nigeria as WPV free
  45 months (as of June 2020) since the last WPV case was detected in Borno State
    Since 2016, all LGAs in Nigeria have consistently reported at least 1 AFP case each year and both surveillance core indicators met by at least 87% of the LGAs yearly
  The system has consistently detected VDPV2 since 2016, across different states. cVDPV2 from AFP cases have also been detected in areas with chronic inaccessibility (due to insurgency): Magumeri (1) and Nganzai (3) LGAs in 2018, Konduga (3) LGA in 2019, all in Borno State
  no WPV has been detected despite the very wide scope of environmental surveillance – 113 ES sites in 29 states, plus the federal capital
A wide-spread, nation-wide cVDPV2 outbreak that began in January 2018 in Jigawa has been largely contained, with two positive detections in one state to date in 2020

## Slide 25: Nigeria Update (cont.)
Source: Borno SPHCDA, GRASPv 8.5
Trend of estimated population in unreached locations from September ‘17 to February ’20 (Number)
Chart: 
 | 248713.916 | 161732 | 149094 | 126717 | 104328 | 102246 | 70541 | 60484 | 43507 | 34210 | 31188
Nov
‘17
Sep ’17
Sep ’16
Oct ’17
Dec ’17
May ’18
Oct ’18
Jun ’19
Feb ’19
Nov ’19
Feb ’20
432,345
-93%
  In a bid to ensure that all children are reached, we use estimates of U-5 children living in locations unreached by any geo-tracked vaccination teams
  However, 385 of the 1,150 locations unreached by geo-tracked teams have tally evidence of reach by RES, RIC and CIIA teams
  These 385 locations account for an estimated 8,539 U-5 children which deducted will bring the estimated number of children in unreached locations to 22,649
  A large number of the U-5 children in unreached locations might have received vaccinations at service points in neighbouring countries
Estimated 93% decrease in U-5 children in settlements unreached by geo-tracked vaccination teams – Borno State, 2016–2020

## Slide 26: cVDPV outbreaks in Africa and Asia
Multiple, continued cVDPV2 outbreaks have been reported in the Africa region, Somalia, Pakistan, Afghanistan, Philippines and Malaysia
Africa: All outbreak response activities were suspended in March 2020 due to COVID-19, leading to a significant expansion outside of areas where mOPV2 response campaigns have taken place, or planned campaigns were postponed
Asia: expansion of cVDPV2 into new geographies in Philippines and Malaysia
The mOPV2 Advisory Group has approved mOPV2 use in Pakistan and Afghanistan, as well as 12 countries in Africa, for a ‘restart’ of outbreak vaccination activities potentially from July 2020
mOPV2 SIAs will also be restarting in Philippines and Somalia

## Slide 27: cVDPV2 summary for the African region (Jan-May 2020)
cVDPV2 Cases and ES, by month
Program
pause
Most of the areas (>80%) were infected in February or earlier.
Country | cVDPV2 (AFP) | cVDPV2 (ENV) | VDPV1 | VDPV2 | Total
ANGOLA | 2 |  |  | 1 | 3
BENIN | 1 |  |  |  | 1
BURKINA FASO | 4 |  |  |  | 4
CAF | 1 | 2 |  | 1 | 4
CAMEROON | 3 | 1 |  |  | 4
CHAD | 13 | 3 |  | 1 | 17
COTE D'IVOIRE | 12 | 29 |  |  | 41
DRC | 6 |  |  |  | 6
ETHIOPIA | 13 |  |  | 1 | 14
GHANA | 12 | 17 |  |  | 29
MALI | 1 |  |  |  | 1
MOZAMBIQUE |  |  | 1 |  | 1
NIGER | 4 |  |  |  | 4
NIGERIA | 1 | 1 |  |  | 2
TOGO | 7 |  |  |  | 7
TOTAL | 80 | 53 | 1 | 4 | 138

## Slide 28
Case
ES+
🡨 Before 2nd SIA
After 2nd SIA 🡪
  Responses are generally effective
    Few cases (<7%) have occurred after 2 mOPV2 SIAs were implemented. 77% of infected districts have had no detections after the 2nd SIA
    Examples of extended breakthrough exist: Haut Lomami, Kwara, around inaccessible areas (Borno, Mogadishu)
mOPV2 Rounds Largely Effective in Stopping most of the cVDPV2 Outbreaks
Notes:
Analysis limited to districts with >90 days of follow-up from the 2nd SIA,
and accessible areas (Borno, Mogadishu removed)
Additional interventions took place (additional mOPV2 SIAs, IPV SIAs)
SIA dates in POLIS often precede implementation

## Slide 29: Preparing for resumption of cVDVP2 activities in Africa
Working groups established by the OPRTT, Regional Offices, and the Africa Rapid Response Team (RRT) to prepare for resumption of activities (i.e. microplanning, budgeting, preparedness tools, deployment management, weekly reporting of activities, vaccine management, C4D, etc)
Country teams including GPEI coordinators, data managers, and others briefed on the updated tools ahead of the planned restart
The Africa RRT in coordination with the Imperial College, Partners, and GPEI coordinators in countries prepared sub-regional risk assessments (see proposed scope of response in the next slide)
The OPRTT, RRT, and Regional offices are monitoring country preparedness to resume activities on a weekly basis, and continuing to provide technical guidance where needed
Surge budgets for July to December 2020 were completed to facilitate recruitment/renewal of contracts
PROPOSED SCOPE OF RESPONSE
targeting approximately 40 million children

## Slide 30
Somalia, Philippines, and Malaysia
Viruses outside mOPV2 response zones – July 2019-May 2020
Country | AFP | ES
Somalia | 0 | 17
Philippines | 1 | 1
Malaysia | 0 | 7
Somalia
cVDPV2 outside response zone*
Philippines and Malaysia
*last mOPV2 response in Somalia in area of virus detection was November 2018
No restart dates for SIAs in Somalia or Malaysia
Philippines targeting 20 July restart for mOPV2 and bOPV

## Slide 31: Communication for cVDPV2 outbreaks and nOPV2
Mitigation
New GPEI Global Communication Group merges external communication (PACT) with C4D and BI for coordinated planning and execution across all levels
Formative research on perceptions of nOPV2 of caregivers, FLWs, and reporters in Africa informed comms planning, products and tools
Crisis communication and scenario building cuts across media response, digital spaces, and FLW preparedness
Standardized outbreak package for field use – modular, quick adaption: Q&As, abridged FLW module and cVDPV2 products for communities and health systems
Risk and Challenges
Aligning global GPEI narrative on cVDPV2 and efforts on the ground: Polio Free Africa, vaccine-derived virus, vaccine naming (positioning)
Novel vaccine under EUL in the context of COVID Infodemics – reputational and vaccine uptake risks beyond Polio
Inadequate capacity to rapidly build immediate public momentum for an outbreak response in 120 days
Notes: Speaker Notes:
Disconnect in GPEI global narrative with programme perception on the ground – explaining cVDPV2 in Africa after certification, “vaccine-derived” viruses name is addressed through more coordinated approach between external communication and C4D branches of GPEI, driven by field knowledge and accounting for global need to maintain donor confidence and support of the programme. A new group brings broad range of communication expertise from GPEI into one stream to align communication strategies and tactics.
Novel OPV2 introduction for cVDPV2 response, a genetically-modified vaccine proposed under emergency use listing in the context of COVID is a challenge on its own. GPEI recognized the communication complexity at various levels, where the vaccine brings new hope to GPEI and donors globally, but positioning this vaccine as “magic bullet” in the field would be counterproductive. GPEI conducted formative research to better understand perceptions and potential concerns of various audiences to come up with right positioning of the Novel OPV2 with tailored messaging based on the need and level of knowledge. Crisis communication in response to vaccine-related events is central and integrated across external and C4D streams of the programme. Using social listening and rumor tracking in digital spaces becoming a more central piece of the programme.
As communication has to stay ahead of the game, there has been traditionally a challenge to build up enough momentum quickly within 14 days before the first round in outbreaks, where existing GPEI capacity is scarce. The programme responded with developing a standard communication package to accompany the SOPs that can quickly be tailored, adapted and used by the Governments and GPEI teams.

## Slide 32: Key messages to the IMB
Spread of cVDPVs might be greater than the current picture due to the pause in outbreak SIAs and surveillance disruptions. There is a need to expand the response scope to get ahead of the virus.
Funding remains a challenge and carrying out polio activities during the COVID-19 pandemic will increase operational costs. GPEI needs to work towards more national funding and ownership.
COVID is likely to be with us for sometime, so there will be a need for ongoing adjustment to polio field operations.
GPEI should take all necessary measures to avoid any more delays in introducing nOPV2.

## Slide 33
Thank You

## Slide 34
Annex

## Slide 35
Additional slides: COVID impact

## Slide 36: Platform & assumptions
I - Emergency Phase (active transmission / rising cases; since April – June 2020?)
- Polio vaccination, along with all mass immunization activities, halted globally
- Critical GPEI function to continue as priority (e.g. PV surveillance)
- Polio staff re-directed in support of pandemic response
- Programmatic impact of COVID-19 requires close monitoring along w/ preparations for Phase II.
II - Resumption Phase (if/when COVID-19 situation allows and/or Polio epidemiology necessitates; July? …): -
- Resumption of polio vaccination to address both outbreaks & WPV eradication, as part of a restart of essential immunization
- Staff pivot back to polio duties.
- Adapt short - medium term strategies, as necessary and identify pathway towards phase III
III – Post/Para - pandemic Phase (time ?):
- Period with significantly lower risk of Covid-19 that permits further expansion of other public health initiatives. Incorporates long-term revisions to the current Polio Endgame Strategy 2019-23
Anticipated COVID-19 Pandemic Evolution

## Slide 37
WPR
SEAR
EUR
EMR
PAH
AFR
Situation as of 29 May 2020 (source: WHE)

## Slide 38: Combined Risk: (Polio Surveillance & COVID-19 (as of 12 June)
38
38
 |  | Polio Risk |  | 
 |  | High | Med-High | Medium
COVID-19 Risk | High | 1 | 3 | 7
 | Medium | 2 | 5 | 8
 | Low | 4 | 6 | 9

## Slide 39
Impact Monitoring & Risk Analysis
Strategic Guidance & coordination
Operational Technical Guidance
GPEI operational planning
Critical Functions Identified to address COVID-19 Impact
Surveillance for Polioviruses
Endemics & Outbreak Response
Prevention SIAs & EI
Coordination

## Slide 40
Impact on Vaccine Supply & Development
Source: WHO
Suspension of SIAs has led to interruption in OPV deliveries
  some suppliers reaching cold chain capacity, and may stop production
Major disruptions of international airfreight & increasing freight rates; & 25 destinations can’t be reached except charters
Delays currently 3 months due to COVID, but for some campaigns to be pushed to 2021 (AFR), shelf life may become an issue both on doses already delivered in the countries, but also for stocks with suppliers due to reduced demand
Closing borders in producing / receiving countries
Impact of reduced demand: Likely very high stock levels globally across suppliers at the end of 2019, increasing the perception of risks of being in the OPV market due to considerable swings in demand, risks of write off due to short shelf life (and risk of future shortage if produced doses are not put to use) increased capital costs tied up in stocks
nOPV2 workstreams progressing but challenges from COVID-19

## Slide 41
Updated GPEI recommendations
(issued 21 May)
WHO/UNICEF/Gavi HoA statement on immunization*
(22 May)
Updated GPEI Continuity Planning Doc.
(issued 16 May)
Framework for decision-making* (issued 22 May)
Field Guides for SIAs Implementation
(end-June / early July?)
Revised SIAs plans for OBs, endemics
(EOMG/OPRTT/ ROs, Hub) End June / early July
May
June
July
GPEI Roadmap for Continuity Planning & Program Ops.
(gradient fill indicates link with EI)
Prev. SIAs?
Outbreak & AFG/PAK SIAs
Guidance on Infection Prevention & Control (IPC)
(29 May)
Strategic & Operational Guidance on preventive SIAs (Polio / VPDs) ??
*gradient fill indicates link w/ EI
Maintaining essential health services (1 June)
Strategic Guidance
Op/ Tech. Guidance
Op. planning
Updated Surv. Guidance
(issued 02 June)
POL Prev. SIAs plan 2020 endorsed

## Slide 42: GPEI Continuity Workplan v1.0, now on GPEI Share Point

## Slide 43: Countries with Polio Activities Postponed due to COVID-19 Pandemic

## Slide 44: Decision Making Model / Framework for Resuming / Implementing Polio SIAs (Annex from Polio Continuity Planning document, May 2020)

## Slide 45: GPEI (UNICEF / WHO) Cost Implications for Supporting COVID-19 (Apr – Jun 2020)
Chart: Cost Implication - for 3 Months (APR, MAY & JUNE)
| AF (40/42) | EM (9/9 ) | EU (0/13 ) | SE (6/6) | WP (2/4) | HQ (1/1)
WHO | 14.4544 | 11.3102 | 0 | 2.1589 | 0 | 0.1748
UNICEF | 1.8897 | 22.5414 | 0 | 0.092451 | 0.26633 | 0

## Slide 46
Additional slides: Africa WPV free certification, Nigeria and Outbreaks

## Slide 47: > 3.5 Years Since WPV Detection in Nigeria
4 WPV1 cases reported in 2016 in Borno State
5 OBR SIA rounds conducted within 5 months, covering 18 states
High quality (around 90% of LGAs surveyed achieved ≥90% LQAS)

## Slide 48
Large gains in vaccination reach, surveillance coverage, and data quality, coupled with drastic changes in population dynamics in Borno, have made ongoing transmission of WPV exceedingly unlikely in Borno and the Lake Chad Basin.
June 2020 ARCC Review
Years since WPV1 detection
Kalkowska DA, et al. Risk Analysis. 2020
Confidence about no circulation given no WPV1 detection (%)

## Slide 49: Decrease in cVDPV2 Detections from 141 in 2018 to two in 2020
2 cVDPV2 detections in Nigeria in 2020, both in Anambra State, Southeast Zone
3 local mOPV2 rounds (September 2019 – February 2020)
Chart: 
| 2018 | 2019 | 2020
AFP | 34 | 18 | 1
ES | 46 | 60 | 1
Contact | 3 | 1 | 0
HC | 58 | 8 | 0
cVDPV2 by Source
1
1
1
cVDPV2 Detections, 2020

## Slide 50
50
Note: 1 VDPV2 from an ES sample collected 18 February 2020 pending classification
mOPV2 SIA
Chart: 
| J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | 2018 | 2019 | 2020
AFP | 1
ES | 1 | 2 | 2 | 5 | 4 | 1 | 2 | 1 | 1 | 2
Contact
HC | 1
cVDPV2 by Source
mOPV2 Campaign Coverage in 2019
Sokoto Risk Assessment: No Need for Additional mOPV2 Outbreak Response Activities
8 May 2020: Three ES samples collected in July, August, September 2019 were reclassified as cVDPV2 after linkage to Niger/Mali
19 May 2020: Sokoto risk assessment concluded no additional mOPV2 OBR required due to 6+ high quality rounds (≥90% LQAS)

## Slide 51
Ongoing cVDPV2 outbreaks in 19 countries
15 countries in Africa, with distinct outbreak foci in West Africa, Chad-Cameroon-CAR, DRC-Angola, Ethiopia, and Somalia
Spread of cVDPV2 outbreak from Pakistan to Afghanistan
Related cVDPV2 and cVDPV1 outbreaks in Philippines and Malaysia
All countries postponed planned mOPV2 and bOPV SIAs by late March and outbreak responses have not resumed
cVDPV positive isolates, Previous 6 months

## Slide 52
Viruses outside mOPV2 response zones: July 2019- May 2020
Jul – Dec 2019 VDPVs Outside Response Zone
Jan-May 2020 VDPVs Outside Response Zone
COUNTRY | cVDPV2 (AFP) | cVDPV2 (ENV) | TOTAL
BENIN | 1 |  | 1
CHAD | 3 |  | 3
COTE D'IVOIRE |  | 7 | 7
DR CONGO | 3 |  | 3
ETHIOPIA | 5 | 2 | 7
TOGO | 1 |  | 1
TOTAL | 13 | 9 | 22
Country | cVDPV2 (AFP) | cVDPV2 (ENV) | VDPV1 | VDPV2 | TOTAL
BURKINA FASO | 2 |  |  |  | 2
CAMEROON | 3 | 1 |  |  | 4
CHAD | 7 |  |  | 1 | 8
COTE D'IVOIRE | 12 | 29 |  |  | 41
DRC | 1 |  |  |  | 1
ETHIOPIA | 6 |  |  | 1 | 7
GHANA | 8 | 1 |  |  | 9
MALI | 1 |  |  |  | 1
MOZAMBIQUE |  |  | 1 |  | 1
NIGER | 4 |  |  |  | 4
TOGO | 5 |  |  |  | 5
TOTAL | 49 | 31 | 1 | 2 | 83

## Slide 53: cVDPV2 lineages in AFRO: 2019 and 2020
Decrease in the number of lineages causing AFP cases in 2020 compared to 2019
NIE-JIS-1 (85) and CHA-NDJ-1 (15) most responsible for continued transmission
2019
2020

## Slide 54
Non-Polio AFP Rate – April 2020 compared to April 2019
Specimen transport delays
Percentage of active ES sites reporting – January-June 2020
AFRO
EMRO
SEARO
Non-polio AFP rates have decreased in April 2020 compared to April 2019
The percentage of ES sites reporting has decreased in March-May 2020 across regions, particularly in AFRO and EMRO
Domestic and International specimen transport delays are impacting countries globally
Source: COVID Flags dashboard (POLIS)

## Slide 55
Immunization: pause in polio SIAs starting March 2020. Many cVDPV2 outbreaks unaddressed
Surveillance: Decreases in NP-AFP rates and delays in sample shipment impair ability to assess risk.
3. Epidemiology: Social distancing measures being relaxed across the Region.
COVID-19 case increase may further delay resumption of campaigns.
AFP Cases Pending Classification
NP-AFP Rate April 2020 compared to April 2019
Source: COVID Flags dashboard (POLIS)
Restart of activities under discussion with countries
Impact of COVID-19 Pandemic in AFRO

## Slide 56: Impact of COVID-19 : Samples pending shipment to GPLN as at 5th June 2020
Country | # AFP samples | # ES samples | Total
Guinea | 161 | 10 | 171
Nigeria | 144 | 38 | 182
Angola | 88 | 27 | 115
Democratic Republic of the Congo | 137 |  | 137
Malawi | 71 |  | 71
Madagascar | 52 |  | 52
Niger | 36 | 8 | 44
Uganda | 34 | 4 | 38
Congo | 24 |  | 24
Benin | 15 | 2 | 17
Gambia | 10 |  | 10
Burkina Faso | 9 | 3 | 12
Equatorial Guinea | 2 | 12 | 14
Mozambique | 12 |  | 12
United Republic of Tanzania | 7 |  | 7
Chad | 7 |  | 7
Eswatini | 4 |  | 4
South Sudan | 4 |  | 4
Gabon | 4 |  | 4
Burundi | 2 |  | 2
Lesotho | 1 |  | 1
Guinea-Bissau | 2 |  | 2
Total | 826 | 104 | 930
Outbreak Countries Pending Samples AFP-826, ES - 104